## Slide 1
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
HR Director | Project Sponsor | H | H | Key decision-maker who approves the budget and scope of the project.
HR Team | Participants | M | H | Direct beneficiaries of the training; their engagement is crucial for project success.
Finance Department | Budget Controller | H | M | Responsible for approving the budget; concerned with financial impact and cost-effectiveness.
IT Department | Technical Support | M | L | Provides technical support for online training platforms; minimal involvement unless technical issues arise.
Senior Management | Strategic Oversight | H | M | Interested in the project’s alignment with organizational goals but not involved in day-to-day activities.
External Vendors | Training Material Suppliers | L | L | Involved in providing training materials; limited power and interest in the project's outcomes.
Stakeholder Analysis

## Slide 2
Stakeholder Analysis
Legal Department | Compliance Advisor | M | M | Ensures that training materials comply with legal and regulatory standards.
Employees (General Staff) | Indirect Beneficiaries | L | L | The training could indirectly impact their payroll and benefits, but they have low power and interest.
Training and Development Team | Training Delivery and Content Development | M | H | Responsible for developing and delivering the training content; critical to project execution.
Union Representatives | Employee Advocates | M | M | May have concerns about changes in salary structures or benefits that could arise from the training.
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes

## Slide 3
Keep satisfied (high priority)
Legal Department
Manage closely (high effort)
HR Director, Senior Management
Finance Department
HR Team, Training and Development Team
Monitor (minimum effort)
-
Show consideration
Union Representatives
IT Department, Employees (General Staff), External Vendors
Power
high
low
med
high
low
stakeholder’s vs
Department
Interest
med

## Slide 4
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Omar
Owner
Drag each stakeholder’s box to the appropriate place on the power-interest grid
Deanna
Director of Operations
Carter
Exec. Chef
Gilly
GM - North
Alex
GM - Downtown
Zane
Kitchen Manager - North
Larissa
Kitchen Manager - Downtown
Seydou
Restaurant Consultant
Interest
med
Nia
General Manager - Waterfront