## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE Five
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
 | time axis 2023-02-06 to 2023-04-29
Milestone: 1 Project Initiation
Create project charter |  | 2023-02-06 | 2023-02-10 | 4 | Peta | 1
Allocate a budget for the project |  | 2023-02-07 | 2023-02-07 | 0 | Peta, Gilly, Alex, Seydou | 1
Schedule kick off meeting |  | 2023-02-08 | 2023-02-08 | 0 | Peta | 1
General Manager meeting with waitstaffs to get buy-in |  | 2023-02-09 | 2023-02-09 | 1 | Peta, Gilly, Alex | 1
Milestone: 2 Preparation
Research tablet features |  | 2023-02-09 | 2023-02-14 | 4 | Seydou | 1
Determine the number of tablets needed |  | 2023-02-10 | 2023-02-10 | 1 | Alex, Gilly | 1
Establish technical requirements (e.g., Wi-Fi, power outlets) |  | 2023-02-10 | 2023-02-13 | 2 | Seydou | 1
Check current POS version |  | 2023-02-13 | 2023-02-14 | 2 | Seydou | 1
Contact electrician |  | 2023-02-14 | 2023-02-14 | 1 | Deanna | 12
Milestone: 3 Vendor Selection
Research and select tablet hardware and software vendors |  | 2023-02-14 | 2023-02-17 | 4 | Seydou | 21
Obtain price quotes and negotiate contracts |  | 2023-02-14 | 2023-02-16 | 3 | Deanna | 22
Confirm compatibility of operating systems to POS system |  | 2023-02-14 | 2023-02-17 | 4 | Seydou | 1
Order the required tablets and software licenses from Terrific Tablets and get it delivered |  | 2023-02-15 | 2023-02-24 | 8 | Deanna | 1
Milestone: 4 Menu Digitization
Revamp the menu | Still waiting on Carter for the finalized menu and coupon value mock-ups for upload | 2023-02-15 | 2023-02-24 | 9 | Carter | 28
Upload menu mock-ups | Once mock-ups are received, 3-4 hours to upload | 2023-02-20 | 2023-02-25 | 5 | Seydou | 29
Record the guest modified menu items |  | 2023-02-23 | 2023-02-24 | 2 | Seydou | 1
Milestone: 5 Tablet Installation
Install the tablets in the restaurant | Seydou projected 7-10 days shipping timeline, 3-4 hours to integrate the POS systems | 2023-02-27 | 2023-03-08 | 8 | Seydou | 2
Wire up the tables | Electrician is confident they can wire both locations in two business days | 2023-02-27 | 2023-03-01 | 3 | Seydou | 4
Connect tablets to the restaurant’s Wi-Fi network |  | 2023-03-01 | 2023-03-01 | 1 | Seydou | 1
Integrate tablets with POS software | Possible need to upgrade the POS system if S&S is running an older version | 2023-03-01 | 2023-03-03 | 3 | Seydou | 1
Test connectivity and functionality |  | 2023-03-06 | 2023-03-08 | 3 | Seydou | 1
Milestone: 6 Staff Training
Create a training schedule | Gilly and Alex will coordinate with Peta to schedule staff trainings at each of their locations | 2023-03-08 | 2023-03-16 | 7 | Gilly, Alex | 1
Pre-training meeting | Pre-training meeting to introduce tablets and changes to staff before training them on the tablets | 2023-03-16 | 2023-03-17 | 2 | Seydou, Deanna, Gilly, Alex | 1
Train key restaurant staff members on tablet usage | Seydou will train managers first (2 hours), then managers will train all the staff at each location | 2023-03-17 | 2023-03-17 | 1 | Gilly, Alex | 1
Troubleshooting common issues |  | 2023-03-20 | 2023-03-20 | 1 | Deanna, Gilly, Alex | 1
Handling customer inquiries about the tablets |  | 2023-03-21 | 2023-03-21 | 1 | Seydou, Gilly, Alex | 1
Train restaurant staffs at each location | Seydou will train managers first (2 hours), then managers will train all the staff at each location | 2023-03-22 | 2023-03-22 | 1 | Gilly, Alex | 1
Milestone: 7 Testing and Quality Assurance
Conduct a test run with family and friends |  | 2023-03-23 | 2023-03-23 | 1 | Deanna, Gilly, Alex, Seydou | 1
Conduct extensive testing of the tablets and menu software |  | 2023-03-23 | 2023-03-24 | 2 | Seydou | 1
Identify and resolve any technical or usability issues |  | 2023-03-24 | 2023-03-27 | 2 | Seydou | 1
Gather feedback from the staff and make necessary adjustments |  | 2023-03-27 | 2023-03-27 | 1 | Peta | 1
Milestone: 8 Marketing and Promotion
Develop a marketing strategy to inform customers about the new tablets |  | 2023-03-27 | 2023-03-29 | 3 | Deanna, Peta | 1
Update the restaurant’s website and social media profiles |  | 2023-03-28 | 2023-03-31 | 4 | Deanna, Peta | 1
Create promotional materials and special offers |  | 2023-03-29 | 2023-03-31 | 3 | Deanna, Peta | 1
Milestone: 9 Launch and Monitoring
Create launch date plan, staffing and troubleshooting |  | 2023-03-30 | 2023-04-07 | 7 | Peta | 1
Officially launch the tablet menu system |  | 2023-03-31 | 2023-03-31 | 1 | Peta | 1
Implement a post-dining survey to assess customer satisfaction |  | 2023-04-03 | 2023-04-03 | 1 | Peta | 1
Address any issues or concerns promptly |  | 2023-04-04 | 2023-04-04 | 1 | Seydou, Peta | 1
Regularly updating the menu via software |  | 2023-04-04 | 2023-04-06 | 3 | Seydou | 1
Continuously assess the performance of the tablets and make improvements as necessary |  | 2023-04-07 | 2023-04-07 | 1 | Seydou | 1
Milestone: 10 Maintenance and Support
Implement a maintenance plan to keep tablets and software up to date |  | 2023-04-10 | 2023-04-17 | 5 | Seydou | 1
Provide ongoing support for staff and customers |  | 2023-04-11 | 2023-04-11 | 1 | Seydou, Gilly, Alex | 1
Regularly assess the impact of the tablets on restaurant operations and customer satisfaction |  | 2023-04-11 | 2023-04-12 | 2 | Peta | 1
Milestone: 11 Evaluation and Reporting
Evaluate the success of the tablet rollout against predefined objectives |  | 2023-04-12 | 2023-04-13 | 2 | Peta | 1
Generate reports on key performance indicators (KPIs) |  | 2023-04-13 | 2023-04-14 | 2 | Peta, Deanna | 1
Make informed decisions for future improvements or expansions |  | 2023-04-14 | 2023-04-14 | 1 | Peta, Deanna | 1
Milestone: 12 Continuous Improvement
Gather ongoing feedback and make necessary adjustments |  | 2023-04-17 | 2023-04-17 | 1 | Peta | 1
Expanding tablet menu to other areas of the restaurant |  | 2023-04-18 | 2023-04-24 | 5 | Seydou, Gilly, Alex | 1
Milestone: 13 Project Closure
Conduct a project review to document lessons learned |  | 2023-04-25 | 2023-04-26 | 2 | Peta | 1
Complete any outstanding administrative tasks |  | 2023-04-27 | 2023-04-27 | 1 | Peta | 1
Celebrate the successful rollout of the tablet menu system |  | 2023-04-28 | 2023-04-28 | 1 | Peta, Deanna | 1

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Create project charter | Peta, as the Project Manager, will handle this. | 5 | 4 | 5 | 7 | H | 2/6/2023 - 2/10/2023
Allocate a budget for the project | Requires input from multiple stakeholders. | 10 | 8 | 10 | 14 | M | 2/7/2023 - 2/7/2023
Schedule kick-off meeting | Peta will coordinate with all involved parties. | 3 | 2 | 3 | 5 | H | 2/8/2023 - 2/8/2023
GM meeting with waitstaff | Collaboration between GMs. | 4 | 3 | 4 | 6 | M | 2/9/2023 - 2/9/2023
Research tablet features | Seydou will conduct this research. | 7 | 5 | 7 | 10 | M | 2/9/2023 - 2/14/2023
Determine the number of tablets needed | Involves multiple restaurant managers. | 4 | 3 | 4 | 6 | M | 2/10/2023 - 2/10/2023
Establish technical requirements | Technical specifications need to be outlined by Seydou. | 5 | 4 | 5 | 7 | M | 2/10/2023 - 2/13/2023
Check current POS version | Seydou will verify POS compatibility. | 2 | 1 | 2 | 4 | H | 2/13/2023 - 2/14/2023
Contact electrician | Deanna will handle the electrician's arrangement. | 3 | 2 | 3 | 5 | M | 2/14/2023 - 2/14/2023
Research and select vendors | Selecting the right vendors is critical. | 10 | 8 | 10 | 14 | M | 2/14/2023 - 2/17/2023
Obtain price quotes | Deanna will negotiate contracts. | 7 | 5 | 7 | 10 | M | 2/14/2023 - 2/16/2023
Order tablets and software | Requires confirmed quotes and approvals. | 5 | 4 | 5 | 7 | H | 2/15/2023 - 2/24/2023
Revamp the menu | Carter, the Exec. Chef, is responsible. | 7 | 5 | 7 | 10 | M | 2/15/2023 - 2/24/2023
Upload menu and coupon mock-ups | Seydou will manage this. | 4 | 3 | 4 | 6 | M | 2/20/2023 - 2/25/2023
Install tablets | Installation across locations managed by Seydou. | 7 | 5 | 7 | 10 | M | 2/27/2023 - 3/8/2023
Train staff on tablet usage | GMs will organize and oversee training. | 5 | 4 | 5 | 7 | M | 3/8/2023 - 3/22/2023
Test run with family and friends | Critical for quality assurance. | 3 | 2 | 3 | 5 | H | 3/23/2023 - 3/23/2023
Conduct extensive testing | Thorough testing needed to ensure functionality. | 7 | 5 | 7 | 10 | M | 3/23/2023 - 3/24/2023
Develop marketing strategy | Collaboratively done by Deanna and Peta. | 10 | 8 | 10 | 14 | M | 3/27/2023 - 3/29/2023
Officially launch the system | Execution of the final launch plan. | 1 | 1 | 1 | 2 | H | 3/31/2023 - 3/31/2023
Post-dining survey | Feedback is essential for improvements. | 3 | 2 | 3 | 5 | M | 4/3/2023 - 4/3/2023
Conduct project review | Final review to capture lessons learned. | 3 | 2 | 3 | 5 | M | 4/25/2023 - 4/26/2023
Integration with POS | Upgrade if necessary | 3 | 2 | 3 | 4 | H | 2023-03-01
Menu digitization | Descriptions, prices | 5 | 3 | 5 | 7 | M | 2023-02-20

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Reservation System Research | N/A | 2018-01-08 | Historical data on booking processes
Project Charter Template | Internal Document | 2023-02-06 | Used for creating the project charter
Tablet Features Research | Internal Report | 2023-02-09 | Research on features needed for tablets
POS System Compatibility | Internal IT Guidelines | 2023-02-13 | Documentation on POS system requirements
Tablet Vendor Quotes | Vendor Emails | 2023-02-14 | Price quotes and negotiation details with vendors
Menu Digitization Guidelines | Internal SOP | 2023-02-15 | Guidelines for revamping and digitizing the menu
Tablet Installation Guide | Internal IT Manual | 2023-02-27 | Procedures for installing and integrating tablets
Staff Training Schedule | Internal Training Document | 2023-03-08 | Schedule for training staff on tablet usage
Marketing Strategy Document | Internal Marketing Plan | 2023-03-27 | Strategy for promoting the new tablet system
Customer Satisfaction Survey Template | Internal Survey Template | 2023-04-03 | Post-launch survey to assess customer satisfaction
Continuous Improvement Plan | Internal Document | 2023-04-17 | Plan for ongoing improvements and feedback
Project Closure Report | Internal Project Report | 2023-04-25 | Documentation for project closure and lessons learned