## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Software Usability(Ease of use for staff) | System should be intuitive and user-friendly | Is the new system easy for staff to use? | Number of support tickets raised by staff | TRUE
Vendor Performance(Adherence to timeline) | Vendors must deliver as per agreed timeline | Did the vendor complete tasks on time? | Percentage of tasks completed on or before the deadline | TRUE
System Reliability (System uptime) | The system should have minimal downtime | How reliable is the system's uptime? | System uptime percentage (e.g., 99.9%) | TRUE
Training Quality (Staff competency) | Staff should be proficient with the new system after training | Are staff confident in using the system? | Post-training assessment scores | TRUE
Installation Quality | Correctness of installation | Were tablets installed correctly? | No issues reported | FALSE
Software Sync | POS system integration | Did the sync work without issues? | Successful transactions | FALSE
Serving Speed | The average ticket time is met. | Are appetizers served quickly? | Appetizers are served within 8 minutes. | FALSE
| The average ticket time is met. | Are the entrees served quickly? | Entrees served within 12-15 minutes. | FALSE
Check-out Speed | Checkout system is fully functional. | Is the checkout process done smoothly? | Checkout done within 1 minute or less. | FALSE
Check-out Process | Checkout system is fully functional. | Is the checkout process seamless? | Checkout done within 1 minute or less. | FALSE
| Checkout system is fully functional. | Are the tablets working efficiently? | Encountered technical issues are less than 2. | FALSE
Order Accuracy | Foods are served completely. | Are the served foods complete? | Order Accuracy is 98%. | FALSE