## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Feedback From | Type | Description | Evidence | Actions
Staff | Feedback | Staff found the tablets easy to use | Survey results | Continue with current model
Customers | Observation | Positive feedback on ordering efficiency | Customer reviews | Promote this feature
Managers | Report | Integration with POS was smooth | Integration logs | Document process
Technicians | Analysis | Minor connectivity issues identified | Technical reports | Improve Wi-Fi setup
Customers | Went well | Majority of the customers had a smooth experience with the new tablets. | 72% of guests rated their experience with the tablets as either 4 (Good) or 5 (Great). | Continue optimizing tablet interface to maintain a positive experience.
Project Team | Needs improvement | Table turn time did not decrease as expected. | Gilly reported that table turn time stayed about the same as before during the retrospective meeting. | Work with GMs to explore strategies for speeding up guest visits and enhancing operational efficiency.
Customers | Needs improvement | Some customers experienced incorrect orders. | 28% of customers reported that their orders were prepared incorrectly. | Enhance the training of kitchen staff and review the technical systems to ensure order accuracy.
Project Team | Went well | Tickets were flowing smoothly through the system. | Zane noted that ticket flow was easy to track. | Maintain current ticket system but continue monitoring for areas of improvement.
Customers | Went well | Majority of the customers ordered appetizers aside from their main dish. | 82% of the customers ordered appetizers
Customers | Went well | Most customers left a good review. | 40% of customers had a good experience with the tablet and 32% with great experience.
Customers | Needs improvement | A little over half of the customers waited for more than 15 mins to get a table. | 54% of the customers waited more than 15 mins in order to get a table. | Discuss how to keep wait times to a maximum of 15 minutes.
Customers | Needs improvement | Some customers experienced receiving wrong orders. | "Here are some of the inaccuracies: - Wrong entree brought out, didn't leave off cheese, or wrong substitution." | Seydou will check technical issues affecting ticket accuracy.
Customers | Went well | Majority of the customers had a smooth checkout process. | 82% of customers found the checkout process quick, easy, and secure.
Customers | Needs improvement | Some customers experienced issues during checkout process. | Some guests noted the tablet froze, and others requested a faster process for paying with a phone or alternate ways. | Seydou will check technical issue on checkout process.
Project Team | Needs improvement | Some food orders were still incorrect and orders were sent back. | There were still orders that got sent back. | Still needs improvement; enhance the training of kitchen staff.
Project Team | Went well | There were improvements in kitchen operations due to the new ticket flow. | Started implementing updates in kitchen operations.
Project Team | Needs improvement | Technical issues during POS integration process. | A few technical issues were discovered during the POS integration but were quickly addressed. | Update process manual so that the solution is easy to find next time.
Customers | Went well | Majority of customers signed up for the newsletter. | 78% of the guests signed up for the newsletter on the tablet.